## Current State Action Items
S/N | Deliverables | Assigned To | Assigned By | Description | DateAssigned | Due Date | Timelines | Priority | Status | Comments
Legal and Government Mandate
1 | Enabling Legislation | Government Integration and Stakeholder Engagement / Board of Directors | Board Directors | Draft and pass a State Law or Executive Order establishing Galaxy ITT | 2025-05-08 | 2025-09-05 | 60–90 days | Critical | In Progress | Draft Bill to be presented to the State Executive Council for consideration.
2 | MEMART Alignment | Government Integration and Stakeholder Engagement | MD/CEO | Update or realign the MEMART with public sector ICT goals | 2025-05-08 | 2025-06-07 | 30 days | High | In Progress | Internal review ongoing; to align with ICT governance standards.
3 | Budget Inclusion | MD / Government Integration and Stakeholder Engagement | MD/CEO | Secure formal inclusion in state budget documents | 2025-05-08 | October 2025 (Q4) | Next budget cycle | High | In Progress | Follow up with Budget Office and Ministry of Finance.
4 | Mandate Publication | Corporate Communications | MD/CEO | Publish mandate and governance details on official platforms | 2025-05-08 | 2025-08-06 | 90 days | Medium | In Progress | Draft mandate not approved; to be uploaded on official website and government portals after approval.
5 | Governance Charter Development | Board Secretariat / Admin | MD/CEO | Develop a governance charter with oversight mechanisms | 2025-05-08 | 2025-07-07 | 60 days | Medium | Completed | Charter finalized and approved by MD/CEO
6 | Regulatory Licensing & Compliance | MD / Legal + ED Technical | MD/CEO | Obtain missing regulatory licenses and compliance certificates | 2025-05-08 | 2025-09-05 | 90–120 days | Medium | In Progress | registration initiated; awaiting regulatory compliance certificates.
Corporate Strategy
1 | Vision, Mission, and Values | MD/CEO + EDs + Strategy Unit | MD/CEO | Develop and validate clear Vision, Mission, and Core Values. | 2025-05-08 | 2025-07-07 | 2 Month | Critical | Completed | Vision, mission, and core values validated by Board Directors and adopted by management.
|  | Corporate Communications + Strategy Unit | MD/CEO | Publish and communicate the Vision and Mission internally and externally. | 2025-05-08 | 2025-07-22 | 2.5 Month | Critical | Completed | Has to be Published internally and on official platforms; communication campaign needed to be initiated.
2 | Strategic Goals and Objectives | Strategy Unit + Heads of Departments | MD/CEO | Define 4-year SMART strategic goals linked to key services and growth. | 2025-05-08 | 2025-08-07 | 3 months | Critical | Completed | 4-year strategic framework finalized and cascaded to Managements and all departments/Units.
|  | Department Heads + Strategy Unit | MD/CEO | Break down goals into Departmental Operational Plans. | 2025-05-08 | 2025-09-07 | 3–4 months | Critical | In Progress | Departmental workplans being aligned with corporate strategy; final integration pending.
3 | Organizational Alignment | Strategy Unit + HR + TA | MD/CEO | Introduce OKRs/KPIs across all departments tied to strategic goals. | 2025-05-08 | 2025-09-07 | 4 months | High | Completed | OKR templates distributed; department KPI alignment sessions finalized.
|  | HR Department | MD/CEO | Link employee appraisal and incentives to departmental OKRs/KPIs. | 2025-05-08 | 2025-10-07 | 5 months | High | In Progress | Draft appraisal framework under HR review; pilot to start next quarter.
4 | Competitive Positioning | Business Development | MD/CEO | Conduct full market and competitor analysis; identify Unique Selling Points (USPs). | 2025-05-08 | 2025-10-07 | 5 months | High | In Progress | Market scan initiated; report due for validation in October 2025.
|  | Strategy Unit + Communications | MD/CEO | Formalize strategic positioning statement and competitive messaging. | 2025-05-08 | 2025-11-07 | 5–6 months | High | In Progress | Branding and messaging needed to be drafted for under review
5 | Stakeholder Engagement | Government Integration and Stakeholder Engagement | MD/CEO | Map key stakeholders; create structured engagement plan (Govt, MDAs, partners). | 2025-05-08 | 2025-05-19 | 2025-05-19 | High | Completed | Stakeholder list compiled; awaiting validation by MD/CEO.
|  | MD/CEO + Strategy Unit | MD/CEO | Schedule quarterly strategic stakeholder forums. | 2025-05-08 | 2025-09-08 | Starting 4th month (ongoing) | Medium | Not started | To commence after mapping validation; first forum scheduled for September 2025.
6 | Resource Alignment | CFO + HR + Strategy Unit | MD/CEO | Conduct resource mapping; realign budgets and staffing to strategic priorities. | 2025-05-08 | 2025-11-07 | 6 months | High | Not started | Resource audit has to be scheduled; alignment with budget and staffing has to be prioritize.
7 | Innovation and Change Readiness | MD/CEO + Strategy Unit + ICT + ED BDS | MD/CEO | Establish Innovation Fund and Innovation Committee. | 2025-05-08 | 2025-11-07 | Within 6 months | High | Not started | Proposal for Innovation Fund has to be prepared; committee members to be nominated.
|  | ICT + Department Heads + ED TS | MD/CEO | Launch 2–3 pilot digital transformation projects. | 2025-05-08 | 2026-02-07 | 6–9 months | High | In Progress | Pilot concepts identified (eGov & Smart Infrastructure); awaiting next stage.
8 | Risk Management | Risk and Compliance Officer + Strategy Unit | MD/CEO | Develop and maintain a Strategic Risk Register and Business Continuity Plan (BCP). | 2025-05-08 | 2025-11-07 | 6 months | High | In Progress | Risk framework has ti be drafted with Risk Officer and Strategy Unit.
9 | Monitoring and Review System | Strategy Unit + Internal Audit | MD/CEO | Set up Quarterly Strategy Implementation Review Meetings. | 2025-05-08 | Start: 07/08/2025 → Quarterly | Start within 3 months (every quarter) | High | Not started | Kick-off meeting planned for August 2025.
|  | Strategy Unit + Communications | MD/CEO | Publish Annual Strategic Progress Report to stakeholders. | 2025-05-08 | 2026-05-07 | Every 12 months | High | Not started | Template need to be design; first annual report due May 2026.
Legal & Regulatory Compliance
10 | Legal Department | MD/CEO + HR | MD/CEO | Establish a Legal & Compliance Unit. Start with personnel on loan or contract. | 2025-05-08 | 2025-06-08 | Immidiate | Critical | In progrees | Legal Unit structure Completed; awaiting to hire or second officers.
11 | Regulatory Compliance | Strategy + Legal | MD/CEO | Register with NITDA and other sector regulators. | 2025-05-08 | 2025-08-07 | 3 months | High | Not started | Registration forms needed to be prepared; and all supporting documentation.
12 | Authority Matrix | MD/Board | MD/CEO | Create and ratify a Delegation of Authority document. | 2025-05-08 | 2025-07-07 | 2 months | High | Not started | Delegation of Authority draft under MD/CEO review.
13 | Tax & Pension Compliance | Finance + HR | MD/CEO | Register with NSITF, PENCOM, and regularize PAYE, WHT, and pension payments. | 2025-05-08 | 2025-07-07 | 1–2 months | High | In Progress | PAYE and PENCOM registration ongoing; partial remittance achieved
14 | Contract Management | Legal + Procurement | MD/CEO | Build contracts register and standard templates (SLA, NDA, MOU). | 2025-05-08 | 2025-08-07 | 3 months | High | In Progress | Standard templates ( SLA, NDA, MOU) in development with Legal & Procurement.
15 | Document Policies | Legal + HR | MD/CEO | Develop internal governance policies: whistleblower, ethics, conflict of interest. | 2025-05-08 | 07/08/2025 – 07/09/2025 | 3–4 months | High | In Progress | Approved by management; training for all departments need to be initiated.
16 | IP Protection | Legal + ICT | MD/CEO | Register trademarks, domain, and software copyrights. | 2025-05-08 | 2025-11-07 | 6 months | High | Not started | Trademark and copyright filings has to be scheduled; domain protection under ICT.
17 | Legal Risk Assessment | Legal + Internal Audit | MD/CEO | Conduct a full legal and regulatory risk assessment. | 2025-05-08 | 2025-09-07 | 4 months | High | Not started | Risk audit to be initiated after full legal team onboarding.
18 | Training | HR + Legal | MD/CEO | Conduct compliance training for all staff and leadership. | 2025-05-08 | 2025-11-07 | 6 months | Medium | Not started | Training plan not be designed by HR & Legal; to start Q4 2025.
Financial Management
19 | Governance | MD/CEO | MD/CEO | Appoint or second a qualified CFO or Finance Manager | 2025-05-08 | 2025-06-08 | Immediate | Medium | In Progress | Interim finance lead appointed; recruitment of full-time CFO ongoing.
20 | Internal Controls | Finance + Strategy | MD/CEO | Develop a Finance Policy Manual and Delegation of Authority Matrix | 2025-05-08 | 2025-06-07 | 1 month | High | In Progress | Draft finance policy framework under development.
21 | Accounting System | Finance + ICT | MD/CEO | Procure and implement accounting software | 2025-05-08 | 2025-07-07 | 2 months | High | Not started | Vendor selection in progress for accounting software
22 | Budgeting & Reporting | Finance + Executive Directors | MD/CEO | Prepare and approve an annual budget, including quarterly reports | 2025-05-08 | 2025-07-07 | 1–2 months | Critical | Not started | 2026 budget drafting has to be initiated by Q4 2025 ; quarterly financial templates has to be developed.
23 | Asset Management | Admin + Finance | MD/CEO | Create a Fixed Asset Register with physical tagging | 2025-05-08 | 2025-07-07 | 2 months | Medium | In Progress | Fixed Asset Register created; assets has to be tagged and verified.
24 | Revenue Model | Finance + Business Dev | MD/CEO | Develop and launch service-based pricing for cloud, hosting, WAN | 2025-05-08 | 2025-08-07 | 3 months | High | Not started | Revenue strategy design to begin after finance automation setup.
25 | Statutory Compliance | HR + Finance | MD/CEO | Register and enroll all staff for PAYE, pension, NSITF | 2025-05-08 | 2025-06-07 | 1 month | High | In Progress | Registration ongoing with state revenue board and PENCOM; NSITF pending.
26 | Financial Audit | MD/CEO + Board | MD/CEO | Commission independent external audit covering past 2–3 years | 2025-05-08 | 2025-08-07 | 3 months | Medium | In Progress | External audit firm engaged; review of FY2022–FY2024 accounts was done.
27 | Payroll Automation | Finance + HR + ICT | MD/CEO | Migrate payroll to digital system with integrated compliance features | 2025-05-08 | 2025-07-07 | 2 months | Critical | In Progress | Migration to digital payroll platform (HR-ICT integrated) at 60% completion.
28 | Board Oversight | CFO/Finance Lead | MD/CEO | Present quarterly financial dashboards to the board or stakeholders | 2025-05-08 | Ongoing (Start: 07/08/2025) | Quarterly | Medium | Continous | First quarterly dashboard presented to board; routine board reviews scheduled for quartely board meeting.
Human Capital and Workforce Capability
29 | Recruit Head of HR | MD/CEO | MD/CEO | Identify, interview, and appoint a qualified HR leader to head the department. | 2025-05-08 | 2025-06-08 | Immediate (0–1 month) | Critical | Completed | HR Lead successfully assigned and assumed duties; department structure defined.
30 | Finalize HR Manual | Admin | MD/CEO | Admin to come out with HR manual outlining policies, procedures, and standards. | 2025-05-08 | 2025-07-07 | 2 months | Critical | Completed | HR manual at drafted; final review has been done, HR needs to submit to the MD/CEO for final approval.
31 | HRIS Acquisition | HR + MD/CEO + TA | MD/CEO | Select and implement a Human Resource Information System for records management. | 2025-05-08 | 2025-08-07 | 2–3 months | Medium | In Progress | Demos completed, awaiting full implementation
32 | Hire for 10 Priority Roles | HR + EDs | MD/CEO | Conduct recruitment for 10 critical roles across departments. | 2025-05-08 | 2025-08-07 | 3 months | Medium | In Progress | Recruitment process in progress.
33 | Launch Performance Management System | HR + MD | MD/CEO | Design and deploy a performance tracking system with KPIs and appraisals. | 2025-05-08 | 2025-09-07 | 4 months | Medium | In Progress | KPI-based performance tool was designed; pilot phase to start in Q4 2025.
34 | Training Plan Deployment | HR + Academy | MD/CEO | Roll out training programs based on staff development needs and job roles. | 2025-05-08 | 2025-11-07 | 4–6 months | Medium | Not started | Training plan needs to be drafted; awaiting HR budget presenation for approval and rollout
35 | Culture & Innovation Programs | HR + Comms | MD/CEO | Initiate staff engagement and innovation programs to improve workplace culture. | 2025-05-08 | 2025-11-07 | 6 months | Medium | Not started | Culture engagement and innovation week planned for November 2025.
Procurement, Logistics and Supply Chain
36 | Procurement Planning | Procurement + Finance + Procurement committee | MD/CEO | Develop and approve an annual procurement plan aligned with budget and strategy. | 2025-05-08 | 2025-06-07 | 30 days | Critical | Not started | Procurement Plan framework needs to be drafted, pending budget approval for 2026.
37 | Tendering Process | Procurement Committee + MDO Office | MD/CEO | Enforce open bidding and establish bid scoring templates and archives. | 2025-05-08 | 2025-07-07 | 2 months | High | Not started | Templates for open bidding needs to be developed; for Procurement Committee review.
38 | Vendor Management | Procurement + Admin | MD/CEO | Create and maintain an Approved Vendor Register with due diligence. | 2025-05-08 | 2025-07-07 | 2 months | Critical | In Progress | Vendor registration ongoing; database will be populated with verified suppliers.
39 | Contract Management | Procurement + Legal (when hired) | MD/CEO | Develop standard templates and formalize milestone-based contracts. | 2025-05-08 | 2025-08-07 | 3 months | High | Not started | Standardized contract templates to be integrated with legal review protocols.
40 | Inventory & Asset Control | Admin + ICT | MD/CEO | Deploy centralized inventory tracking and update fixed asset register. | 2025-05-08 | 2025-08-07 | 3 months | High | Not started | Central inventory system yet to be deployed; manual records currently in use.
41 | Logistics & Warehousing | Admin + Technical Ops | MD/CEO | Establish logistics plans for all major projects and secure warehouse space. | 2025-05-08 | 2025-09-07 | 3–4 months | Medium | Not started | Warehouse space identified; layout and security plan under preparation.
42 | Policy Framework | Procurement + Strategy | MD/CEO | Draft and approve procurement and asset disposal policies. | 2025-05-08 | 2025-08-07 | 3 months | Critical | In Progress | Draft policy expected to be approved by August 2025.
43 | Contract Enforcement | MD/CEO | MD/CEO | Engage a legal officer (loaned or hired) to review contracts. | 2025-05-08 | 2025-06-08 | Immediate | Critical | In Progress | Legal officer assigned on interim basis to support contract validation and enforcement.
44 | Digital Systems | ICT + Procurement + ED TS | MD/CEO | Use Excel or simple eProcurement tools to manage bids and inventory. | 2025-05-08 | 2025-11-07 | 6 months | Medium | Not started | Evaluation of low-cost procurement management software.
45 | Ethics & Controls | Internal Audit + HR | MD/CEO | Document segregation of duties and ethics policy; conduct refresher training. | 2025-05-08 | 2025-08-07 | 2–3 months | Medium | Not started | Policy design for ethics and segregation of duties pending HR and Audit inputs.
Business Development and Revenue Generation
46 | Strategic Direction | ED Business Development | MD/CEO | Develop 3-year BD & marketing strategy | 2025-05-08 | 2025-07-07 | 1 month | High | In Progress | Strategic framework has to be developed; for approval and execution.
47 | CRM | ICT + BD | MD/CEO | Acquire and implement a basic CRM tool | 2025-05-08 | 2025-08-06 | 1 month | High | In Progress | Rollout Data collection targeting ICT sector and e-Government service for opportunities.
48 | Market Segmentation | BD Unit | MD/CEO | Define top 3 focus verticals (government, SMEs, education) | 2025-05-08 | 2025-08-06 | 1 month | High | In Progress | Service offerings outlined; awaiting alignment with infrastructure rollout.
49 | Sales Infrastructure | BD + Procurement | MD/CEO | Build template library (proposal, pitch deck, bid forms) | 2025-05-08 | 2025-09-05 | 1 month | High | Not started | Revenue streams to be modeled around hosting, cloud, and fiber services.
50 | Service Packaging | BD + Product Dev | MD/CEO | Define pricing models, SLAs, and product brochures | 2025-05-08 | 2025-08-06 | 1–2 months | High | In Progress | Partnership discussions ongoing
51 | Revenue Targets | ED Business Development | MD/CEO | Set quarterly goals by segment and region | 2025-05-08 | 2025-08-06 | Monthly | Critical | In Progress | Sales & Marketing team to design outreach plan by Q4 2025.
52 | Donor & Tech Partners | MD/CEO + BD | MD/CEO | Identify 5 partners (e.g., USPF, Huawei, Cisco) for co-investment | 2025-05-08 | 2025-07-07 | 3 months | High | In Progress | Branding strategy needs to be drafted and executed; new corporate identity will be rolled out across platforms.
53 | Website & Digital Media | Marketing Unit | MD/CEO | Rebuild the website and launch awareness campaigns | 2025-05-08 | 2025-08-07 | 1–2 months | High | Completed | CRM vendor needs to be identified; pilot deployment expected by August 2025.
54 | Capacity Building | HR + ED,BDS | MD/CEO | Train BD and Sales teams on account management, solution selling | 2025-05-08 | 2025-11-07 | 3 months | High | In Progress | MoUs needs to be drafted and negotiated with tech vendors and ICT innovation hubs.
Technical Infrastructure and Systems
55 | Infrastructure Recovery | Technical Ops + Admin | MD/CEO | Restore and upgrade State Secretariat server room. Build interim Tier II hosting capability. | 2025-05-08 | 2025-08-07 | 1–3 months | High | In Progress | Structural upgrade at 60%; power stabilization completed; awaiting final network cabling and rack setup.
56 | Cloud Stack Deployment | Technical Ops + Strategy | MD/CEO | Acquire and deploy a private cloud stack (e.g., Zadara). | 2025-05-08 | 2025-11-07 | 3–6 months | High | Not started | Procurement proposal under review; implementation expected in Q4 2025.
57 | Security Enhancement | ICT + Security Officer | MD/CEO | Implement NGFW, EDR/XDR, RBAC, and encryption tools. Create a formal IRP. | 2025-05-08 | 2025-08-07 | 3 months | Critical | Not started | Security assessment conducted; procurement of security tools pending approval.
58 | Monitoring Tools | Technical Ops | MD/CEO | Deploy NOC/SOC solution with dashboards, logging, and bandwidth analytics. | 2025-05-08 | 07/07/2025 – 07/09/2025 | 2–4 months | High | In Progress | NOC dashboard design completed; test environment setup ongoing.
59 | Documentation & Policies | ICT + Internal Audit | MD/CEO | Develop IT policies, SOPs, disaster recovery, and network diagrams. | 2025-05-08 | 2025-08-07 | 3 months | High | In Progress | Draft IT policy framework in ptogress; DR and SOPs under review.
60 | Ticketing and Helpdesk | ICT + HR | MD/CEO | Implement an open-source or low-cost ITSM platform for service management. | 2025-05-08 | 07/06/2025 – 07/07/2025 | 1–2 months | High | In Progress | Open-source helpdesk (GLPI) selected; installation and HR integration in progress.
61 | Talent Acquisition | HR + Executive Directors | MD/CEO | Recruit system admins, network engineers, cybersecurity staff. | 2025-05-08 | 2025-06-08 | Immediate | Critical | In Progress | Recruitment drive ongoing
62 | Training and Certification | HR + Technical Training | MD/CEO | Initiate Galaxy ITT Academy training for cloud, security, and systems roles. | 2025-05-08 | 2025-08-07 | 3 months | Medium | In Progress | Training curriculum needs to be drafted; first cohort expected to begin in August 2025.
63 | VSAT Service Activation | BD + Technical Ops | MD/CEO | Partner with satellite providers to commercialize VSAT assets in rural LGAs,. | 2025-05-08 | 07/07/2025 – 07/08/2025 | 2–3 months | High | In Progress | Partnership discussions ongoing; pilot deployment expected by August 2025.
Project Management and Implementation Maturity
64 | Project Governance | MD/CEO + Strategy Unit + ICT + ED TSD | MD/CEO | Establish a formal PMO with defined structures and roles | 2025-05-08 | 2025-07-07 | 1–2 months | High | Not started | PMO framework and organogram drafted; appointment of Head of PMO pending approval.
65 | Planning Discipline | PMO + All Departments + ED TSD | MD/CEO | Require charters, workplans, resource maps, and risk registers | 2025-05-08 | 07/07/2025 – 07/08/2025 | 2 months | Medium | In Progress | Draft governance template aligned with NITDA standards; review by legal Unit.
66 | Tools & Templates | ICT + PMO + ED TSD | MD/CEO | Deploy a basic project tracking tool and standardized templates | 2025-05-08 | 07/06/2025 – 07/07/2025 | 1–2 months | Medium | In Progress | Open-source PM tool (OpenProject) needs to be selected; configuration and training aterwards.
67 | Financial Oversight | Finance + PMO | MD/CEO | Enforce milestone-based payments and introduce cost tracking | 2025-05-08 | 07/07/2025 – 07/08/2025 | 2–3 months | Critical | In Progress | Dashboard prototype needs to be presented; awaiting integration with PM tools.
68 | Stakeholder Engagement | BD + PMO | MD/CEO | Create and mandate post-implementation reports and handovers | 2025-05-08 | 2025-08-07 | 2 months | High | In Progress | To commence after PMO operationalization.
69 | Closure Protocols | PMO + ICT | MD/CEO | Create and mandate post-implementation reports and handovers | 2025-05-08 | 2025-09-07 | 3 months | High | In Progress | To commence after PMO operationalization.
70 | Skills Development | HR + PMO | MD/CEO | Train staff in PRINCE2 or PMBOK fundamentals | 2025-05-08 | 2025-10-07 | 4 months | High | Not started | Training modules developed; to commence after PMO operationalization.
Internal Processes and Operational Controls
71 | Process Identification & Mapping | Head of Strategy / COO + TA | MD/CEO | Conduct a comprehensive process identification and mapping exercise across all departments. | 2025-05-08 | 2025-08-07 | Within 3 months | Medium | Completed | Mapping concluded; documentation submitted for SOP alignment.
72 | SOP Development | Process Owners + Strategy Unit + HR | MD/CEO | Develop Standard Operating Procedures (SOPs) for all core processes. | 2025-05-08 | 2025-11-07 | 3–6 months | High | Completed | SOP manual finalized and distributed to all departments.
73 | Ownership Assignment | MD/CEO + EDs + Department Heads | MD/CEO | Assign a Process Owner for each identified business process. | 2025-05-08 | 2025-06-07 | Immediate (Within 1 month) | Critical | In Progress | Ownership assignment ongoing; 70% of departments completed
74 | Workflow Optimization | Process Owners + Strategy Unit | MD/CEO | Redesign workflows to remove duplication and reduce manual steps. | 2025-05-08 | 2026-02-07 | 6–9 months | Medium | Completed | Process optimization completed; automation stage next.
75 | Process Automation | Head of ICT | MD/CEO | Deploy a simple BPM (Business Process Management) system or upgrade existing ERP modules. | 2025-05-08 | 2026-05-07 | 9–12 months | Medium | Not started | Awaiting budget to start for BPM software procurement inclusion
76 | KPI & Metrics Definition | Head of Strategy + Process Owners | MD/CEO | Establish clear KPIs and performance indicators for each process. | 2025-05-08 | 2025-11-07 | 6 months | Medium | In Progress | KPI draft prepared; validation by MD/CEO pending.
77 | Process Training | HR Department + Process Owners | MD/CEO | Train all employees on the new SOPs and process flows. | 2025-05-08 | 2026-02-07 | After SOP approval; within 6–9 months | Medium | In Progress | To commence after full SOP and KPI implementation.
78 | Process Monitoring | Internal Audit Unit | MD/CEO | Set up regular process monitoring and audit routines | 2025-05-08 | Continuous | Quarterly | High | Not started | To commence after full SOP and KPI implementation.
79 | Feedback Mechanisms | Strategy Unit + HR | MD/CEO | Introduce regular process feedback collection (surveys, focus groups). | 2025-05-08 | 2025-11-07 | Start within 6 months | Medium | Not started | To commence after full SOP and KPI implementation.
80 | Continuous Improvement Culture | Managemen Team | MD/CEO | Launch a "Process Excellence Initiative" to reward innovation in processes. | 2025-05-08 | 2026-05-07 | Within 9–12 months | Medium | Not started | To be launched after first performance review cycle.
Physical Security
81 | Perimeter Upgrade | Admin / Procurement | MD/CEO | Replace wire fence with brick/mortar or steel fencing | 2025-05-08 | 2025-08-07 | Within 90 days | High | Not started | Design and cost evaluation completed; awaiting budget approval and contractor mobilization.
82 | Security Contractor Engagement | Management / Legal | MD/CEO | Engage a licensed private security outfit and police unit | 2025-05-08 | 2025-06-07 | Immediate | High | Not started | Vendor shortlist completed; final selection expected in Q4 2025.
83 | Guard Management System (Phase 1) | Management / Legal | MD/CEO | Deploy a guard management system (shifts, logging) | 2025-05-08 | 2025-06-07 | Immediate | Medium | Completed | Fully functional; daily security attendance
84 | Guard Management System (Phase 2) | Admin / HR | MD/CEO | Deploy a guard management system (shifts, logging) | 2025-05-08 |  | 60 days | Medium |  | Fully functional; daily security attendance
85 | SOC / Control Room Setup | Technical | MD/CEO | Setup a proper SOC or control room for monitoring CCTV | 2025-05-08 | 2025-07-07 | 90 days | High | Not started | Equipment procurement underway; installation planned for November 2025.
87 | Incident Response & Evacuation Plan | MD/CEO + Admin | MD/CEO | Develop and enforce an incident response and evacuation plan | 2025-05-08 |  | 60 days | High | In progress | Plan drafted and under review; simulation exercise scheduled for December 2025.
88 | Security Training & Drills | HR / External Security Partner | MD/CEO | Conduct security training and drills for all personnel | 2025-05-08 | 2025-07-07 | Quarterly | Medium | Continous | Drills conducted quarterly; next refresher scheduled for January 2026.
89 | Site Signage & Emergency Contacts | Admin + T.A | MD/CEO | Post visible signage and emergency contacts around the site | 2025-05-08 | 2025-06-07 | 30 days | Medium | Completed | Signage installed at all Galaxy ITT offices
90 | Fire Response Kit & Asset Tracking | Admin / ICT / T.A | MD/CEO | Maintain a fire response kit and asset tracking system | 2025-05-08 | 2025-06-07 | 45 days | High | Completed | Fire kits inspected and restocked

## ED-TS
S/N | Deliverables | Assigned To | Assigned By | Description | DateAssigned | Due Date | Timelines | Priority | Status | Comments
1 | Infrastructure Recovery | Technical Ops + Admin | MD/CEO | Restore and upgrade State Secretariat server room. Build interim Tier II hosting capability. | 2025-05-08 | 2025-08-07 | 1–3 months | High | In Progress | Structural upgrade at 60%; power stabilization completed; awaiting final network cabling and rack setup.
2 | Cloud Stack Deployment | Technical Ops + Strategy | MD/CEO | Acquire and deploy a private cloud stack (e.g., Zadara). | 2025-05-08 | 2025-11-07 | 3–6 months | High | Not started | Procurement proposal under review; implementation expected in Q4 2025.
3 | Security Enhancement | ICT + Security Officer | MD/CEO | Implement NGFW, EDR/XDR, RBAC, and encryption tools. Create a formal IRP. | 2025-05-08 | 2025-08-07 | 3 months | Critical | Not started | Security assessment conducted; procurement of security tools pending approval.
4 | Monitoring Tools | Technical Ops | MD/CEO | Deploy NOC/SOC solution with dashboards, logging, and bandwidth analytics. | 2025-05-08 | 07/07/2025 – 07/09/2025 | 2–4 months | High | In Progress | NOC dashboard design completed; test environment setup ongoing.
5 | Documentation & Policies | ICT + Internal Audit | MD/CEO | Develop IT policies, SOPs, disaster recovery, and network diagrams. | 2025-05-08 | 2025-08-07 | 3 months | High | In Progress | Draft IT policy framework in ptogress; DR and SOPs under review.
6 | Ticketing and Helpdesk | ICT + HR | MD/CEO | Implement an open-source or low-cost ITSM platform for service management. | 2025-05-08 | 07/06/2025 – 07/07/2025 | 1–2 months | High | In Progress | Open-source helpdesk (GLPI) selected; installation and HR integration in progress.
7 | Talent Acquisition | HR + Executive Directors | MD/CEO | Recruit system admins, network engineers, cybersecurity staff. | 2025-05-08 | 2025-06-08 | Immediate | Critical | In Progress | Recruitment drive ongoing
8 | Training and Certification | HR + Technical Training | MD/CEO | Initiate Galaxy ITT Academy training for cloud, security, and systems roles. | 2025-05-08 | 2025-08-07 | 3 months | Medium | In Progress | Training curriculum needs to be drafted; first cohort expected to begin in August 2025.
9 | VSAT Service Activation | BD + Technical Ops | MD/CEO | Partner with satellite providers to commercialize VSAT assets in rural LGAs,. | 2025-05-08 | 07/07/2025 – 07/08/2025 | 2–3 months | High | In Progress | Partnership discussions ongoing; pilot deployment expected by August 2025.

## ED-BD
S/N | Deliverables | Assigned To | Assigned By | Description | DateAssigned | Due Date | Timelines | Priority | Status | Comments
1 | Strategic Direction | ED Business Development | MD/CEO | Develop 3-year BD & marketing strategy | 2025-05-08 | 2025-07-07 | 1 month | High | In Progress | Strategic framework has to be developed; for approval and execution.
2 | CRM | ICT + BD | MD/CEO | Acquire and implement a basic CRM tool | 2025-05-08 | 2025-08-06 | 1 month | High | In Progress | Rollout Data collection targeting ICT sector and e-Government service for opportunities.
3 | Market Segmentation | BD Unit | MD/CEO | Define top 3 focus verticals (government, SMEs, education) | 2025-05-08 | 2025-08-06 | 1 month | High | In Progress | Service offerings outlined; awaiting alignment with infrastructure rollout.
4 | Sales Infrastructure | BD + Procurement | MD/CEO | Build template library (proposal, pitch deck, bid forms) | 2025-05-08 | 2025-09-05 | 1 month | High | Not started | Revenue streams to be modeled around hosting, cloud, and fiber services.
5 | Service Packaging | BD + Product Dev | MD/CEO | Define pricing models, SLAs, and product brochures | 2025-05-08 | 2025-08-06 | 1–2 months | High | In Progress | Partnership discussions ongoing
6 | Revenue Targets | ED Business Development | MD/CEO | Set quarterly goals by segment and region | 2025-05-08 | 2025-08-06 | Monthly | Critical | In Progress | Sales & Marketing team to design outreach plan by Q4 2025.
7 | Donor & Tech Partners | MD/CEO + BD | MD/CEO | Identify 5 partners (e.g., USPF, Huawei, Cisco) for co-investment | 2025-05-08 | 2025-07-07 | 3 months | High | In Progress | Branding strategy needs to be drafted and executed; new corporate identity will be rolled out across platforms.
8 | Website & Digital Media | Marketing Unit | MD/CEO | Rebuild the website and launch awareness campaigns | 2025-05-08 | 2025-08-07 | 1–2 months | High | Completed | CRM vendor needs to be identified; pilot deployment expected by August 2025.
9 | Capacity Building | HR + ED,BDS | MD/CEO | Train BD and Sales teams on account management, solution selling | 2025-05-08 | 2025-11-07 | 3 months | High | In Progress | MoUs needs to be drafted and negotiated with tech vendors and ICT innovation hubs.

## T.A
S/N | Deliverables | Assigned To | Assigned By | Description | DateAssigned | Due Date | Timelines | Priority | Status | Comments
1 | Process Identification & Mapping | Head of Strategy / COO + TA | MD/CEO | Conduct a comprehensive process identification and mapping exercise across all departments. | 2025-05-08 | 2025-08-07 | Within 3 months | Medium | Completed | Mapping concluded; documentation submitted for SOP alignment.
2 | SOP Development | Process Owners + Strategy Unit + HR | MD/CEO | Develop Standard Operating Procedures (SOPs) for all core processes. | 2025-05-08 | 2025-11-07 | 3–6 months | High | Completed | SOP manual finalized and distributed to all departments.
3 | Ownership Assignment | MD/CEO + EDs + Department Heads | MD/CEO | Assign a Process Owner for each identified business process. | 2025-05-08 | 2025-06-07 | Immediate (Within 1 month) | Critical | In Progress | Ownership assignment ongoing; 70% of departments completed
4 | Workflow Optimization | Process Owners + Strategy Unit | MD/CEO | Redesign workflows to remove duplication and reduce manual steps. | 2025-05-08 | 2026-02-07 | 6–9 months | Medium | Completed | Process optimization completed; automation stage next.
5 | Process Automation | Head of ICT | MD/CEO | Deploy a simple BPM (Business Process Management) system or upgrade existing ERP modules. | 2025-05-08 | 2026-05-07 | 9–12 months | Medium | Not started | Awaiting budget to start for BPM software procurement inclusion
6 | KPI & Metrics Definition | Head of Strategy + Process Owners | MD/CEO | Establish clear KPIs and performance indicators for each process. | 2025-05-08 | 2025-11-07 | 6 months | Medium | In Progress | KPI draft prepared; validation by MD/CEO pending.
7 | Process Training | HR Department + Process Owners | MD/CEO | Train all employees on the new SOPs and process flows. | 2025-05-08 | 2026-02-07 | After SOP approval; within 6–9 months | Medium | In Progress | To commence after full SOP and KPI implementation.
8 | Process Monitoring | Internal Audit Unit | MD/CEO | Set up regular process monitoring and audit routines | 2025-05-08 | Continuous | Quarterly | High | Not started | To commence after full SOP and KPI implementation.
9 | Feedback Mechanisms | Strategy Unit + HR | MD/CEO | Introduce regular process feedback collection (surveys, focus groups). | 2025-05-08 | 2025-11-07 | Start within 6 months | Medium | Not started | To commence after full SOP and KPI implementation.
10 | Continuous Improvement Culture | Managemen Team | MD/CEO | Launch a "Process Excellence Initiative" to reward innovation in processes. | 2025-05-08 | 2026-05-07 | Within 9–12 months | Medium | Not started | To be launched after first performance review cycle.

## HR
S/N | Deliverables | Assigned To | Assigned By | Description | DateAssigned | Due Date | Timelines | Priority | Status | Comments
1 | Recruit Head of HR | MD/CEO | MD/CEO | Identify, interview, and appoint a qualified HR leader to head the department. | 2025-05-08 | 2025-06-08 | Immediate (0–1 month) | Critical | Completed | HR Lead successfully assigned and assumed duties; department structure defined.
2 | Finalize HR Manual | HR & Admin | MD/CEO | Admin to come out with HR manual outlining policies, procedures, and standards. | 2025-05-08 | 2025-07-07 | 2 months | Critical | Completed | HR manual at drafted; final review has been done, HR needs to submit to the MD/CEO for final approval.
3 | HRIS Acquisition | HR & Admin + MD/CEO + TA | MD/CEO | Select and implement a Human Resource Information System for records management. | 2025-05-08 | 2025-08-07 | 2–3 months | Medium | In Progress | Demos completed, awaiting full implementation
4 | Hire for 10 Priority Roles | HR & Admin + EDs | MD/CEO | Conduct recruitment for 10 critical roles across departments. | 2025-05-08 | 2025-08-07 | 3 months | Medium | In Progress | Recruitment process in progress.
5 | Launch Performance Management System | HR & Admin + MD | MD/CEO | Design and deploy a performance tracking system with KPIs and appraisals. | 2025-05-08 | 2025-09-07 | 4 months | Medium | In Progress | KPI-based performance tool was designed; pilot phase to start in Q4 2025.
6 | Training Plan Deployment | HR + Academy | MD/CEO | Roll out training programs based on staff development needs and job roles. | 2025-05-08 | 2025-11-07 | 4–6 months | Medium | Not started | Training plan needs to be drafted; awaiting HR budget presenation for approval and rollout
7 | Culture & Innovation Programs | HR + Comms | MD/CEO | Initiate staff engagement and innovation programs to improve workplace culture. | 2025-05-08 | 2025-11-07 | 6 months | Medium | Not started | Culture engagement and innovation week planned for November 2025.
8 | Perimeter Upgrade | Admin / Procurement | MD/CEO | Replace wire fence with brick/mortar or steel fencing | 2025-05-08 | 2025-08-07 | Within 90 days | High | Not started | Design and cost evaluation completed; awaiting budget approval and contractor mobilization.
9 | Security Contractor Engagement | Management / Legal | MD/CEO | Engage a licensed private security outfit and police unit | 2025-05-08 | 2025-06-07 | Immediate | High | Not started | Vendor shortlist completed; final selection expected in Q4 2025.
10 | Guard Management System (Phase 1) | Management / Legal | MD/CEO | Deploy a guard management system (shifts, logging) | 2025-05-08 | 2025-06-07 | Immediate | Medium | Completed | Fully functional; daily security attendance
11 | SOC / Control Room Setup | Technical | MD/CEO | Setup a proper SOC or control room for monitoring CCTV | 2025-05-08 | 2025-07-07 | 90 days | High | Not started | Equipment procurement underway; installation planned for November 2025.
12 | Incident Response & Evacuation Plan | MD/CEO + Admin | MD/CEO | Develop and enforce an incident response and evacuation plan | 2025-05-08 |  | 60 days | High | In progress | Plan drafted and under review; simulation exercise scheduled for December 2025.
13 | Security Training & Drills | HR / External Security Partner | MD/CEO | Conduct security training and drills for all personnel | 2025-05-08 | 2025-07-07 | Quarterly | Medium | Continous | Drills conducted quarterly; next refresher scheduled for January 2026.
14 | Site Signage & Emergency Contacts | Admin + T.A | MD/CEO | Post visible signage and emergency contacts around the site | 2025-05-08 | 2025-06-07 | 30 days | Medium | Completed | Signage installed at all Galaxy ITT offices
15 | Fire Response Kit & Asset Tracking | Admin / ICT / T.A | MD/CEO | Maintain a fire response kit and asset tracking system | 2025-05-08 | 2025-06-07 | 45 days | High | Completed | Fire kits inspected and restocked

## Gov.Int & SE
S/N | Deliverables | Assigned To | Assigned By | Description | DateAssigned | Due Date | Timelines | Priority | Status | Comments
1 | Enabling Legislation | Government Integration and Stakeholder Engagement / Board of Directors | Board Directors | Draft and pass a State Law or Executive Order establishing Galaxy ITT | 2025-05-08 | 2025-09-05 | 60–90 days | Critical | In Progress | Draft Bill to be presented to the State Executive Council for consideration.
2 | MEMART Alignment | Government Integration and Stakeholder Engagement | MD/CEO | Update or realign the MEMART with public sector ICT goals | 2025-05-08 | 2025-06-07 | 30 days | High | In Progress | Internal review ongoing; to align with ICT governance standards.
3 | Budget Inclusion | MD / Government Integration and Stakeholder Engagement | MD/CEO | Secure formal inclusion in state budget documents | 2025-05-08 | October 2025 (Q4) | Next budget cycle | High | In Progress | Follow up with Budget Office and Ministry of Finance.
4 | Stakeholder Engagement | Government Integration and Stakeholder Engagement | MD/CEO | Map key stakeholders; create structured engagement plan (Govt, MDAs, partners). | 2025-05-08 | 2025-08-06 | 2025-05-19 | High | In Progress | Draft mandate not approved; to be uploaded on official website and government portals after approval.
5 | Stakeholder Forums | MD/CEO + Strategy Unit | MD/CEO | Schedule quarterly strategic stakeholder forums. | 2025-05-08 | 2025-09-08 | Starting 4th month (ongoing) | Medium | Not started | To commence after mapping validation; first forum scheduled for September 2025.

## Analysis
Status | Count | Percentage
Completed | 15 | 19.5%
In Progress | 35 | 45.5%
Not Started | 25 | 32.5%
Continuous/Ongoing | 2 | 2.6%